## Sheet1
|  | Hrs/student | Diff Level | Student 1 | Student 2 | Student 3 | Student 4
1 | Requirements (Clarification) (group based)
| - With Composite items | 4 | 3 | 4 | 4 | 4 | 4
| - With Work flow | 4 | 3 | 4 | 4 | 4 | 4
| - With Advanced Applications | 4 | 3 | 4 | 4 | 4 | 4
2 | Web/Tablet UI Design
| - Home page with common UI template and style | 16 | 2 | 16 |  |  | 16
| - A basic dashboard or tracking function to monitor completion and performance. | 16 | 2 | 16 |  |  | 16
| - Simple navigation functions for students to access available worksheets | 16 | 2 | 16 |  |  | 16
3 | Database modeling
| - Designing the tables and fields (MySQL) | 32 | 2 |  | 32
4 | Worksheet Design
| - An interface for students to access and complete interactive worksheets related to critical thinking (e.g., identifying cause and effect, pattern recognition, social reasoning). | 8 | 2 | 8 |  | 8
| - Include visual supports, simple text, multiple choice options, and drag-and-drop elements. | 32 | 3 |  |  | 32
| - Upload / download function for teachers | 8 | 3 |  |  | 8
| - Admin panel for teacher/coach to add, edit, or assign worksheets | 16 | 3 |  | 16
| - Worksheets structured around key cognitive skills (e.g., cause-effect reasoning, pattern matching, visual problem-solving) | 16 | 2 | 16 | 16 | 16 | 16
5 | Web App for Report Analysis and Forecasting
| -Report Analysis | 16 |  |  |  | 16
| -Summary of staff movement across locations | 8 |  | 8
6 | System Testing (group based)
| - Functional Testing | 8 | 2 | 8 | 8 | 8 | 8
| - Integration testing | 16 | 3 |  | 16 |  | 16
7 | System Documentation / Report
| - Final Report & Documentations | 8 | 2 | 8 | 8 | 8 | 8
| - Presentation preparation | 8 | 2 | 8 | 8 | 8 | 8
| - A1 poster for project exhibition | 4 | 2 | 4 | 4 | 4 | 4
|  |  |  | 120 | 120 | 120 | 120